## VENDOR INFO
Contractor Information |  | Example
Vendor Number:
Vendor Name: |  | General Mechanical
Vendor Address: |  | 2701 S. J. St. Tacoma, WA 98409
Spec No: | PW22-0295N
Contract No:
PO No:
Description: | Speed Limit Changes
Inspector: |  | Bill Billings
Payment Period Thru: |  | 30

## BIDTABSUM
Prepare the bid tabs on "BIDTAB" worksheet.
Unfreeze panes and copy/paste the complete bid tab to this sheet and hide unnecessary rows and columns to fit on one page.

## PAYEST
City of Tacoma
Engineering Division
Periodic Payment Estimate No. 01
Payment Period: x/x/xxxx to x/x/xxxx
PAYMENT TO: ,
PROJECT NO: Specification No: PW22-0295N / Contract No: / PO Number:
DESCRIPTION: Speed Limit Changes
Item | Description | Unit | Tax | Original Contract Quantity | Quantity to Date | Unit Price | Amount To Date | Previous Est. | Present Est. | Authorized Project Limit | $ Over/Under | % Over/Under
1 | Mobilization | LS |  | 1 | 0 | 40164.8 | 0 | 0 | 0 | 40164.8 | -40164.8 | -100%
2 | Project Temporary Traffic Control | LS |  | 1 | 0 | 15742.8 | 0 | 0 | 0 | 15742.8 | -15742.8 | -100%
3 | Remove Wood Post & Sign | EA |  | 61 | 0 | 103.7 | 0 | 0 | 0 | 6325.7 | -6325.7 | -100%
4 | Remove Sign from Utility Pole | EA |  | 31 | 0 | 106.4 | 0 | 0 | 0 | 3298.4 | -3298.4 | -100%
5 | Remove Old Speed Limit Sign from Existing Metal Post | EA |  | 55 | 0 | 69.2 | 0 | 0 | 0 | 3806 | -3806 | -100%
6 | Remove Old Speed Limit Signs from Existing Street Light Poles | EA |  | 110 | 0 | 68 | 0 | 0 | 0 | 7480 | -7480 | -100%
7 | Furnish & Install Metal Post & New 20 MPH Speed Limit Sign | EA |  | 26 | 0 | 663.2 | 0 | 0 | 0 | 17243.2 | -17243.2 | -100%
8 | Furnish & Install New 20 MPH Speed Limit Sign (Street Light Pole Mounted) | EA |  | 15 | 0 | 253.34 | 0 | 0 | 0 | 3800.1 | -3800.1 | -100%
9 | Temporary Bagging New 20 MPH Speed Limit Sign and Uncover on Effective Date | EA |  | 41 | 0 | 102.8 | 0 | 0 | 0 | 4214.8 | -4214.8 | -100%
10 | Furnish/Install/Replace Metal Post & New 25 MPH Speed Limit Sign (Metal Post Mounted) | EA |  | 115 | 0 | 663.2 | 0 | 0 | 0 | 76268 | -76268 | -100%
11 | Furnish/Install/Replace 25 MPH Speed Limit Sign (Street Light Pole Mounted) | EA |  | 77 | 0 | 253.3 | 0 | 0 | 0 | 19504.1 | -19504.1 | -100%
12 | Furnish/Install/Replace Metal Post & New "XX" MPH Speed Limit Sign (Metal Post Mounted) | EA |  | 20 | 0 | 663.2 | 0 | 0 | 0 | 13264 | -13264 | -100%
13 | Furnish/Install/Replace "XX" MPH Speed Limit Sign (Street Light Pole Mounted) | EA |  | 4 | 0 | 253.3 | 0 | 0 | 0 | 1013.2 | -1013.2 | -100%
14 | Furnish & Install New Metal Post & New Default Gateway Notice Signs (Post Mounted) | EA |  | 32 | 0 | 879.8 | 0 | 0 | 0 | 28153.6 | -28153.6 | -100%
15 | Furnish & Install New Default Gateway Notice Signs (Street Light Pole Mounted) | EA |  | 3 | 0 | 697.4 | 0 | 0 | 0 | 2092.2 | -2092.2 | -100%
16 | Furnish & Install New Metal Post & New Neighborhood Business District Sign (Post Mounted) | EA |  | 10 | 0 | 300 | 0 | 0 | 0 | 3000 | -3000 | -100%
17 | Furnish & Install New Neighborhood Business District Sign (Street Light Pole Mounted) | EA |  | 10 | 0 | 402 | 0 | 0 | 0 | 4020 | -4020 | -100%
18 | Temporary Removal and Reinstall of Existing Parking and Traffic Control & Warning Signs | EA |  | 83 | 0 | 118.9 | 0 | 0 | 0 | 9868.7 | -9868.7 | -100%
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
#REF! | #REF! | #REF! |  | #REF! | 0 | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
| SUB-TOTAL - Bid Items | [5 empty] | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
CHANGE ORDERS
RFC #
[5 empty] | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL - Change Orders | [5 empty] | 0 | 0 | 0 |  | 0
| GRAND TOTALS | [5 empty] | #REF! | 0 | #REF! | #REF! | #REF! | #REF!
| Informational Only-Taxable Totals | [5 empty] | #REF! | #REF! | #REF!
|  | Amount To Date | Previous Est. | Present Est. |  |  | Council Authorization | Base | Sales Tax | Total
| CONTRACT TOTAL BEFORE TAX | #REF! | 0 | #REF! |  |  | Original | 0 | 0 | 0
| SALES TAX: 9.5% | 0 | 0 | 0 |  |  | Supplement Amount | 0 | 0 | 0
| GRAND TOTALS | #REF! | 0 | #REF! |  |  | Total Authorized | 0 | 0 | 0
| RETAINAGE: 5% | #REF! | 0 | #REF! |  |  | Spent to Date | #REF! | 0 | #REF!
[7 empty] | Council Authorized Funds Available | #REF! | 0 | #REF!
| NET TOTAL AMOUNTS | #REF! | 0 | #REF!
| LESS AMOUNT PREVIOUSLY PAID | 0
| LESS LIQUIDATED DAMAGES | 0
| TO BE PAID THIS ESTIMATE | #REF!
I certify, to the best of my knowledge, that the above is based on actual measurements and is true and correct, and that all | [9 empty] | Current
the work included above has been performed in accordance with the plans and specifications. | [6 empty] | WBS No. | Gross | Retainage | Payment Due
[8 empty] | #REF! | #REF! | #REF!
[8 empty] | #REF! | #REF! | #REF!
[8 empty] | #REF! | #REF! | #REF!
Prepared By Audrey Scales, Financial Assistant, Engineering Division |  |  |  |  | Date
Mark Henry, Public Works Engineering Division |  |  |  |  | Date

## BIDTAB
Description: Speed Limit Changes
Specification No.: PW22-0295N
Bid Opening: 9/23/22
|  |  |  | ENGINEER'S |  | Low Bidder |  | #2 Bidder
|  |  |  | ESTIMATE |  | Axum General Construction, Inc |  | KT Contracting
Item | Description | Unit | Quantity | Unit Price | Amount | Unit Price | Amount | Unit Price | Amount
1 | Mobilization | LS | 1 | 10000 | 10000 | 40164.8 | 40164.8 | 25843 | 25843
2 | Project Temporary Traffic Control | LS | 1 | 2500 | 2500 | 15742.8 | 15742.8 | 61674 | 61674
3 | Remove Wood Post & Sign | EA | 61 | 2500 | 152500 | 103.7 | 6325.7 | 64 | 3904
4 | Remove Sign from Utility Pole | EA | 31 | 75 | 2325 | 106.4 | 3298.4 | 69 | 2139
5 | Remove Old Speed Limit Sign from Existing Metal Post | EA | 55 | 75 | 4125 | 69.2 | 3806 | 65 | 3575
6 | Remove Old Speed Limit Signs from Existing Street Light Poles | EA | 110 | 75 | 8250 | 68 | 7480 | 64 | 7040
7 | Furnish & Install Metal Post & New 20 MPH Speed Limit Sign | EA | 26 | 355 | 9230 | 663.2 | 17243.2 | 605 | 15730
8 | Furnish & Install New 20 MPH Speed Limit Sign (Street Light Pole Mounted) | EA | 15 | 130 | 1950 | 253.34 | 3800.1 | 283 | 4245
9 | Temporary Bagging New 20 MPH Speed Limit Sign and Uncover on Effective Date | EA | 41 | 5 | 205 | 102.8 | 4214.8 | 57 | 2337
10 | Furnish/Install/Replace Metal Post & New 25 MPH Speed Limit Sign (Metal Post Mounted) | EA | 115 | 355 | 40825 | 663.2 | 76268 | 678 | 77970
11 | Furnish/Install/Replace 25 MPH Speed Limit Sign (Street Light Pole Mounted) | EA | 77 | 130 | 10010 | 253.3 | 19504.1 | 251 | 19327
12 | Furnish/Install/Replace Metal Post & New "XX" MPH Speed Limit Sign (Metal Post Mounted) | EA | 20 | 355 | 7100 | 663.2 | 13264 | 630 | 12600
13 | Furnish/Install/Replace "XX" MPH Speed Limit Sign (Street Light Pole Mounted) | EA | 4 | 130 | 520 | 253.3 | 1013.2 | 285 | 1140
14 | Furnish & Install New Metal Post & New Default Gateway Notice Signs (Post Mounted) | EA | 32 | 436 | 13952 | 879.8 | 28153.6 | 763 | 24416
15 | Furnish & Install New Default Gateway Notice Signs (Street Light Pole Mounted) | EA | 3 | 211 | 633 | 697.4 | 2092.2 | 455 | 1365
16 | Furnish & Install New Metal Post & New Neighborhood Business District Sign (Post Mounted) | EA | 10 | 355 | 3550 | 300 | 3000 | 636 | 6360
17 | Furnish & Install New Neighborhood Business District Sign (Street Light Pole Mounted) | EA | 10 | 130 | 1300 | 402 | 4020 | 365 | 3650
18 | Temporary Removal and Reinstall of Existing Parking and Traffic Control & Warning Signs | EA | 83 | 75 | 6225 | 118.9 | 9868.7 | 132 | 10956
| GRAND TOTAL |  |  |  | 275200 |  | 259259.6 |  | 284271
| EIC = Less Sales Tax |  |  |  | 275200 |  | 259259.6 |  | 284271
* Correction made to Bid Item Total and/or Bid Total Amount

## PAYFOLDER
Description: Speed Limit Changes
Contractor:
Inspector: | [5 empty] | DATE WORK COMPLETED TO
Payment Period Thru: th of the month |  |  |  |  | / / | / / | / / | / / | / / | / /
[5 empty] | EST NO 1 | EST NO 2 | EST NO 3 | EST NO 4 | EST NO 5 | EST NO 6
Item | Description | Unit | Quantity | Unit Price | Amount | Amount | Amount | Amount | Amount | Amount
1 | Mobilization | LS | 1 | 40164.8 | [6 empty] | 1 | 40164.8
2 | Project Temporary Traffic Control | LS | 1 | 15742.8 | [6 empty] | 2 | 15742.8
3 | Remove Wood Post & Sign | EA | 61 | 103.7 | [6 empty] | 3 | 6325.7
4 | Remove Sign from Utility Pole | EA | 31 | 106.4 | [6 empty] | 4 | 3298.4
5 | Remove Old Speed Limit Sign from Existing Metal Post | EA | 55 | 69.2 | [6 empty] | 5 | 3806
6 | Remove Old Speed Limit Signs from Existing Street Light Poles | EA | 110 | 68 | [6 empty] | 6 | 7480
7 | Furnish & Install Metal Post & New 20 MPH Speed Limit Sign | EA | 26 | 663.2 | [6 empty] | 7 | 17243.2
8 | Furnish & Install New 20 MPH Speed Limit Sign (Street Light Pole Mounted) | EA | 15 | 253.34 | [6 empty] | 8 | 3800.1
9 | Temporary Bagging New 20 MPH Speed Limit Sign and Uncover on Effective Date | EA | 41 | 102.8 | [6 empty] | 9 | 4214.8
10 | Furnish/Install/Replace Metal Post & New 25 MPH Speed Limit Sign (Metal Post Mounted) | EA | 115 | 663.2 | [6 empty] | 10 | 76268
11 | Furnish/Install/Replace 25 MPH Speed Limit Sign (Street Light Pole Mounted) | EA | 77 | 253.3 | [6 empty] | 11 | 19504.1
12 | Furnish/Install/Replace Metal Post & New "XX" MPH Speed Limit Sign (Metal Post Mounted) | EA | 20 | 663.2 | [6 empty] | 12 | 13264
13 | Furnish/Install/Replace "XX" MPH Speed Limit Sign (Street Light Pole Mounted) | EA | 4 | 253.3 | [6 empty] | 13 | 1013.2
14 | Furnish & Install New Metal Post & New Default Gateway Notice Signs (Post Mounted) | EA | 32 | 879.8 | [6 empty] | 14 | 28153.6
15 | Furnish & Install New Default Gateway Notice Signs (Street Light Pole Mounted) | EA | 3 | 697.4 | [6 empty] | 15 | 2092.2
16 | Furnish & Install New Metal Post & New Neighborhood Business District Sign (Post Mounted) | EA | 10 | 300 | [6 empty] | 16 | 3000
17 | Furnish & Install New Neighborhood Business District Sign (Street Light Pole Mounted) | EA | 10 | 402 | [6 empty] | 17 | 4020
18 | Temporary Removal and Reinstall of Existing Parking and Traffic Control & Warning Signs | EA | 83 | 118.9 | [6 empty] | 18 | 9868.7
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF!
Date Verified
Inspector's Initials
Contractor's Initials